## Product - Release Tracking
Product Backlog - Product - Release Tracking Release ID: QTAD-PBL / 2.0.0 / 30-Mar-2015 C3: Protected Controlled Copy Project ID: Car Pooling System <SCI.ID> / Ver: <No.>
Release Iteration # | Release Start Date | Release End Date | Estimated Effort for Release (person days) | Team Size For Release | Estimated Velocity For Release (FCP/Features) | Feature Set ID | Feature ID | Feature Name | Assigned to | Dependency of Feature | Original Scope | Planned Sprint Iteration # | Initial Estimate For Feature (person days) | Revised Estimate For Feature (person days) | Feature Status | Calculated Fields
[16 empty] | Original Features - Completed (person days) | New Features - Not Completed (person days) | New Features -Completed (person days)
1 | 2019-03-07 | 2019-03-11 | 5 | 5 | 0.428 | FS_1 | FEA_1.1 | User Registration |  | User being able to enter the mandatory details and Register himself for accessing the system | X | Sprint 1 | 6 | 6 | Complete | 6 | 0 | 0
2 | 2019-03-11 | 2019-03-13 | 3 | 5 | 0.428 | FS_2 | FEA_1.2 | User Authentication |  | The details entered by the User being authenticated and confirmed on the registration. | X | Sprint 1 | 6 | 6 | Complete | 6 | 0 | 0
3 | 2019-03-13 | 2019-03-15 | 3 | 5 | 0.714 | FS_3 | FEA_2.1 | Post ride |  | User being able to post a ride for pooling. | X | Sprint 1 | 9 | 9 | Complete | 9 | 0 | 0
4 | 2019-03-18 | 2019-03-20 | 3 | 5 | 0.714 | FS_4 | FEA_3.1 | Match Vicinity |  | System being able to to match people within vicinity. | X | Sprint 2 | 11 | 11 | Inprogress | 0 | 0 | 0
5 | 2019-03-20 | 2019-03-22 | 3 | 5 | 1.14 | FS_5 | FEA_4.1 | Notify user |  | System being able to notify the matched people to get connected for the ride. | X | Sprint 2 | 6 | 6 | Complete | 6 | 0 | 0
6 | 2019-03-22 | 2019-03-24 | 3 | 5 | 1.857 | FS_6 | FEA_5.1 | Request ride |  | User being able to request for a ride for pooling. | X | Sprint 3 | 9 | 9 | Inprogress | 0 | 0 | 0
0
7 | 2019-03-24 | 2019-03-25 | 2 | 5 | 0.714 | FS_7 | FEA_6.1 | Bill the ride |  | System being able to calculate the amount for ride. | X | Sprint 3 | 3 | 3 | Complete | 3 | 0 | 0
0